## Slide 1
AI Enablement Initiative
ODC Practice Professional Services delivery team
28th August 2025

## Slide 2: AI Enablement Initiative
  Objective:
  Prepare ODC (OSM, DevOps and Cybersecurity) Professional Services delivery team in India to be able to confidently position and deliver AI solutions.
  High Level Plan & Goals:
Phase 1
Plan: Provide basic knowledge of AI and OT ODC Aviators through online self learning as per recommended curriculum
Phase 2
Plan: In depth portfolio specific learning of OT Aviator solution through instructor led classroom sessions, Shadow projects
Phase 3
Plan: Developer level enablement for AI through mentoring & lab access, build prototype AI solutions / use cases as a group
Duration: 2 months
Duration: 2 months
Timeline: M3Q1 to M1Q2 (Sept, Oct 2025)
Timeline: M3Q2 to early M1Q3 (Dec 2025, Jan 2026)
Duration: 4 months
Timeline: M3Q3 to M3Q4 (March – June 2026)
Goal: General AI Awareness
Goal: Design and deliver OT ODC Aviator solution
Goal: Build new use cases and AI applications to complement standard Aviator offerings
Note: Expected time investment – 4 to 5 hours every week. 1 month gap planned between each phase to provide further flexibility.

## Slide 3: Enablement Strategy
  Phase 1: General AI enablement
    Introduction and program overview – Instructor led session
    AI fundamentals – Self paced trainings on Google partner portal or Microsoft covering basic concepts of AI. Optional courses available in Udemy for more detailed learning.
    Weekly sessions with mentors to seek clarifications. Weekly quiz to check progress and encourage learning.
    OT OAC AI Solution Overview – Instructor led session(s) to introduce OT OAC Aviator solutions
    Industry-recognized certification: Ex: Google - Introduction to Generative AI
  Phase 2: Portfolio specific enablement
    Learn: Portfolio specific Aviator enablement for OSM, DevOps, Cybersecurity through classroom training
    Certification: OT Aviator certification (when available)
    Practice: Customer demos for OOTB Aviator capabilities, shadow participation in AI projects
  Phase 3: Advanced AI enablement
    Learn: Generative AI for Developers courses in Google portal or Microsoft
    Practice: Work as a group on internal AI initiatives and develop prototypes
    Participate in AI projects: Work on actual customer projects

## Slide 4: Phase 1
General AI enablement

## Slide 5: Phase 1 - General / Common Enablement
Topic | Method | Duration | Details
Introduction & Program Overview | Teams Meeting | 1.5 Hrs | Introducing initiative, resources available etc.
OT Aviator Overview | Recording | 1.5 Hrs | Overview of all OT Aviator products
OSM Aviator | Teams Meeting | 1 Hr | SMAX & OpsB Aviator – interactive session
DevOps Aviator | Teams Meeting | 30 min | Value Edge Aviator – interactive session
Cybersecurity Aviator | Teams Meeting | 30 min | Fortify Aviator – Interactive session
AI fundamentals (Essential) | Self paced trainings on Google partner portal | Appx 5 Hrs | Generative AI Fundamentals – 30 min Introduction to Large Language Models – 1 hr Generative AI for Business Leaders – 1 Hr 45 Min Introduction to Vertex AI Studio – 2 Hrs
AI fundamentals (Additional) | Self paced trainings on Google partner portal | Appx 15 Hrs | Text Prompt Engineering Techniques – 8 Hrs Introduction to Responsible AI – 30 min Responsible AI Applying AI Principles with Google Cloud – 2 Hrs Boost Productivity with Gemini in BigQuery – 4 Hrs Final Quiz – Generative AI Fundamentals – 30 minutes

## Slide 6: Phase 1 - Execution Plan Sample (Using Google learning portal)
Week 1
(Introduction)
Week 8
Attempt Certification
Week 3
Day 1 - Introduction to Generative AI Studio
Week 2
(AI Fundamentals Essentials - Self learning Google portal)
  Day 1 –Value Edge & Fortify Aviator – Interactive sessions
  Day 2 - Generative AI fundamentals, Introduction to LLM
  Day 3 - Generative AI for Business leaders
Week 5 to week 6
Text Prompt Engineering Techniques
Week 7
Revisions of key learnings, share experience with others, seek clarifications from mentors
Day 3 – OSM Aviator – Interactive sessions
Day 2 – OT Aviator Solution Overview
Day 1 – Enablement overview session
Week 4
Boost productivity with Gemini in BigQuery
Day 2 - Introduction to responsible AI
Day 3 – Applying AI principles with Google cloud
Time investment – Appx 4 to 5 Hours every week. Interactive sessions will be planned on alternate days. Self learning can be done as per flexible timings.
Estimated duration – 8 weeks.
Self learning – Google partner portal - Introduction to Generative AI | Google Cloud Skills Boost for Partners
Outcome: Provide overview of OT Aviator solution through Online sessions.
Outcome: Understanding of AI fundamentals.
Weekly catch up sessions
Weekly sessions with mentors to seek clarifications and guidance.
Revision session. Seek clarification from mentors
Obtain Google certification / Badge – Intro to gen AI

## Slide 7: Phase 1 – Additional Material (Internal)
  Landing page for all internal Aviator resources - opentext.ai – OpenText Central
  Using AI Tools – OpenText Navigator
  OllieAI training videos : https://corporateit.opentext.com/ollie-ai/
  MyAviator for OllieAI : Watch the video
      Create your own personal workspaces and add your own content to use with Aviator​
      Link to other areas of OllieAI like the Customer Use Case library and Product​
  Aviator blogs - Welcome to opentext.ai - OpenText Blogs

## Slide 8: Phase 1 – Additional Material (External)
  FREE self-guided AI training courtesy of our partners at Microsoft
    Visit https://esi.microsoft.com/landing
    Enter your OpenText email address. ​Agree with the ESI Learning Opportunities Agreement. ​Select your learning preferences.
  FREE self-guided AI fundamentals training, courtesy of our partners at Google
    To access the Google Cloud Skills Boost site, please visit https://partner.cloudskillsboost.google ​
    If you have not done so previously, click “Join” to create an account. ​On the following screen, make sure to use/enter your OpenText email address.
  There are certifications also available in both the online learning portals
  Udemy courses – require approvals from manager. Fill up the form in PS academy for consultants. Once approved access Udemy using your OpenText email ID.

## Slide 9: Phase 2
Portfolio specific enablement

## Slide 10: Phase 2 - Domain Specific Enablement
Topic | Method | Details
OSM Aviator | 1) Self learning through earlier training sessions, access to labs 2) Instructor Led classroom training | Recorded enablement sessions & presentation - Microsoft Teams (IT Operations Aviator enablement) 2 to 3 shared labs to be provided to practice 2) Classroom session – reinforce learning and to clarify doubts 3 days classroom session – 11 topics with lab for 5 topics (>60%) and demo of Aviators <Refer slide 7>
DevOps (ValueEdge) Aviator | 1) Self Paced courses 2) Instructor Led | Recorded enablement – ALM Aviator Training Instructor led classroom session
Cybersecurity Aviator | 1) Self Paced courses 2) Instructor Led | Self learning – 6 topics of 2 hours each <Refer slide 8> Instructor led classroom session

## Slide 11: Phase 2 - SMAX Aviator Classroom Training Topics
Introduction of SMAX Aviator – Day 1: 1 Hr
AI Use cases & Capabilities – Day 1: 1.5 Hrs
Aviator Service Architecture & deployment options, customer onboarding (Lab: Integrate your SMAX tenant with SMAX Aviator trial instance) – Day 1: 3 Hrs
Aviator Models (Lab: Try OOTB models, Try building new models) – Day 1: 2 Hrs
Aviator Business Rules, Workflows, Sentiment Analysis (Lab: Creating sentiment analysis aviator model) – Day 2: 2 Hrs
Change risk analysis (Lab: Create risk score aviator model) – Day 2: 1 Hr
Integrating enterprise content (Lab: Install and configure IDOL connector for SharePoint) - Day 2: 2 Hrs
SMAX Aviator licensing & pricing Day 2: 1 Hr
Introduction to OpsB Aviator Use cases & Capabilities – 2 Hr
OpsB Aviator deployment scenarios, licensing – 1 Hr
Demo – 2 Hr
Product roadmap – 1 Hr

## Slide 12: Phase 2 - Cybersecurity AI Training Topics (Self learning) – Machine Learning
Lecture 1 Introduction 2h
Lecture 2 Network detection and unsupervised learning 2h
Lecture 3 Malware detection and supervised learning 2h
Lecture 4 DGA Detection and NLP – Part I 2h
Lecture 5 Software vulnerability detection and NLP – Part 2 2h
Lecture 6 Synthetic data generation and generative methods 2h
More courses to be added later.
Phase 2 - DevOps AI Training Materials (Self learning)
ALM (AQM) Aviator Recorded Training - OpenText™ Core Share
ValueEdge 101: Adding Aviator AI – Talent Central - Learning
More courses to be added later.

## Slide 13: Phase 3
Advanced AI enablement – Generative AI for Developers

## Slide 14: Phase 3 - Generative AI for Developers
Intermediate level Courses -
Building Gen AI Apps with Vertex AI: Prompting and Tuning – Appx 13 Hrs
Explore Generative AI with the Vertex AI Gemini API – Appx 5 Hrs
Vector Search and Embeddings – 2 Hrs
Inspect Rich Documents with Gemini Multimodality and Multimodal RAG – 5 Hrs
Integrate Vertex AI Search and Conversation into Voice and Chat Apps – 5 Hrs
Orchestrate LLM solutions with LangChain – 4 Hrs
Build Generative AI Apps with Firebase Genkit – 6 Hrs
Advanced Courses (On individual interest basis)
Empower Gen AI apps with tool use – 6 Hrs
Integrate Generative AI Into Your Apps with Firebase Genkit – 6 Hrs
Develop Advanced Enterprise Search and Conversation Applications – 8 Hrs
Deploy, Test & Evaluate Gen AI Apps – 6 Hrs
Orchestrating Gen AI Applications with LangChain – 9 Hrs
Custom Search with Embeddings in Vertex AI – 8 Hrs